## Testing Road Map
Team 1 - Testing Scope
|  |  | Test Cycle 1 | Test Cycle 2 | Test Cycle 3
Xero Application Modules | Feature Backlog (from RCT) | Story Points | Execution Ends - April 25 | Execution Ends - May 3 | Execution Ends - May 10
01. Dashboard
02. User Management and Authentication
03. Settings and Configuration
04. Financial Data Entry
05. Bank Feeds and Reconciliations
06. Invoicing
07. Accounts Receivable
08. Purchase Orders
| 8.01 Managing Vendors/Suppliers | 3 | X
| 8.02 Creating Item/Product Catalog | 2 | X
| 8.03 Creating Purchase Order | 4 |  | X
| 8.04 Approving Purchase Order | 3 |  | X
| 8.05 Tracking Purchase Order | 2 |  |  | X
09. Expense Claims | 8.06 Managing Documents | 3 |  | X |  | Story Point Breakdown
| 9.01 Capturing and Analyzing Receipts | 4 | X
| 9.02 Submitting and Approving Expenses | 3 |  | X |  | 1-2 Points → Simple CRUD operations
| 9.03 Categorizing Expenses | 3 |  |  | X
| 9.04 Consolidate Payments | 4 | X |  |  | Basic create, update, delete actions.
| 9.05 Approve Expenses | 3 |  | X |  | Example: Creating an item/product catalog, managing vendors/suppliers.
| 9.06 Handle Multiple Currencies | 4 |  |  | X
10. Bills to Pay | 9.07 Integrate Payroll | 3 |  | X |  | 3 Points → Moderate complexity
| 10.01 Creating Bill | 2 | X
| 10.02 Processing the Payment | 3 |  | X |  | Tasks that involve workflows, approvals, or basic calculations.
| 10.03 Tracking Expenses | 3 |  |  | X | Example: Submitting and approving expenses, tracking purchase orders.
| 10.04 Automating Recurring Bills | 4 | X
11. Accounts Payable | 10.05 Managing Customer Credit Note | 3 |  | X |  | 4 Points → Complex features with data processing
| 11.01 Administer Billing & Invoices | 4 |  |  | X
| 11.02 Oversee Supplier & Cost Management | 3 | X |  |  | Requires handling multiple data points, scheduling, or reports.
| 11.03 Implement Automation & Integrations | 4 |  | X |  | Example: Categorizing expenses, automating recurring bills, consolidating payments.
| 11.04 Enforce Security & Compliance | 4 |  |  | X
12. Accounting Reports | 11.05 Handle Payment Processing | 3 | X |  |  | 5 Points → High-effort tasks (integrations, automation, financial calculations)
Involves external systems, APIs, or heavy processing.
Example: Handling multiple currencies, processing payments, enforcing security and compliance.
|  | VELOCITY: | 25 | 29 | 20